{"text_format":"2","workbook":"xlsx","n_sheets":2,"sheets":["软件系统框架","问题清单"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":0,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"软件系统框架","index":0,"n_rows":18,"n_cols":3,"rows_kept":18,"cut":false,"hidden":false,"merged":[[0,0,0,2],[1,0,2,0],[5,0,7,0],[10,0,15,0],[12,1,13,1],[14,1,15,1],[16,0,17,0]]}
["软件系统框架"]
["感测系统","入口地面雷达"]
[null,"夹持杆安全雷达"]
[]
[]
["控制系统","检查节点"]
[null,"入队节点"]
[null,"调度管理","数据库"]
[]
[]
["前端系统","终端界面","号牌机"]
[null,"投影引导"]
[null,"出口模块","出口单片机"]
[null,null,"出口LED"]
[null,"入口模块","入口LED"]
[null,null,"入口单片机"]
["后台监控","流程监控"]
[null,"车位管理"]

{"sheet":"问题清单","index":1,"n_rows":15,"n_cols":5,"rows_kept":15,"cut":false,"hidden":false,"merged":[]}
[null,"问题清单","解决办法",null,"时间"]
[]
["感测系统","雷达检测的稳定性, 雷达容易误报","后续考虑优化算法,识别障碍物.\n报告汇报","曾志文"]
[null,"7号多线雷达损坏. 导致C2入口无法使用","尽快购买","曾志文"]
[]
["入口终端","有时程序直接崩溃","找bug","王康","2022-12-30"]
[null,"终端提示信息, 弹窗故障信息需要优化","列举弹窗信息,打印提交曾总","王康","2022-12-27"]
[]
["入口投影","投影提示信息, 逻辑需要优化","修改逻辑后光电无遮挡且没有一帧正常的静止数据,提示入口被干扰,","曾志文","2022-12-30"]
[]
["出入口单片机转发控制","数据库操作不稳定,容易崩溃, ","修改逻辑:删除指令两次不成功,销毁对象,重新创建.\n后续并入调度,(重写)","胡力","2022-12-28"]
[]
["车位监控","数据库操作不稳定,容易崩溃","安装python调试环境,调试运行找原因","王康","2022-12-28"]
["系统测试","列举测试清单","现场测试存档","胡力","2022-12-30"]
["总入口加显示屏",null,"正在开发中","王康"]