{"text_format":"2","workbook":"xlsx","n_sheets":2,"sheets":["说明","2023"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":0,"comments":1,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"说明","index":0,"n_rows":9,"n_cols":2,"rows_kept":9,"cut":false,"hidden":false,"merged":[[0,0,0,1]]}
["小组月度计划/报告填写说明"]
[1,"计划的制定和执行是一个不断细化的过程；"]
[2,"月计划、周计划和日计划的区别在于时间控制的粒度不同；"]
[3,"正常情况下，月度计划与周计划、日计划有相同的任务范围；"]
[4,"月度计划由组长负责制定，月度计划的时间控制粒度为周，因此，制定月度计划时，直接将任务填写到本月相应的周计划中；"]
[5,"在实施某个周计划之前，组长须根据情况将周计划做必要的细化分解，组员根据小组的周计划将个人的任务分解到天，填写到个人的周计划中；"]
[6,"在计划实施过程中，组长须根据实际情况调整本周后面的周计划，如将后面的周计划任务提前实施，或在后面的周计划中插入新的任务；"]
[7,"在计划实施过程中，组长重点关注计划的执行情况，协助组员解决好关键路径上的任务，注意防范风险；"]
[8,"每周计划中未完成的任务（包括计划的、临时添加的、提出的问题和建议）需要标红，以便以后追踪。"]

{"sheet":"2023","index":1,"n_rows":37,"n_cols":12,"rows_kept":37,"cut":false,"hidden":false,"merged":[[0,0,0,11],[3,0,3,11],[7,0,10,0],[7,2,10,2],[12,2,14,2],[11,0,14,0],[29,2,32,2],[33,0,36,0],[34,2,36,2],[27,0,27,11],[2,0,2,11],[5,0,5,11],[17,0,20,0],[17,2,20,2],[21,0,24,0],[22,2,24,2],[15,0,15,11],[29,0,32,0]]}
["软件感测部门工作计划"]
[]
["状态代码：C- 已完成；I- 进展中；X- 未开始；D- 延期已完成；"]
["一、计划任务情况及执行情况"]
["项目","序号","任务名称","详细说明","技术路线","检验标准","计划开始时间","计划完成时间","实际完成时间","完成情况","负责人","备注"]
[]
[null,null,"2022-11-28"]
["感测系统",1,"设计方案","完成设计方案初稿",null,null,"2022-12-27","2022-12-27","2022-12-27","I"]
[null,{"$f":"B8+1","v":2},null,"设计方案讨论及修改",null,null,"2022-12-27","2022-12-27","2022-12-27"]
[null,{"$f":"B9+1","v":3},null,"设计方案定稿",null,null,"2022-12-27","2022-12-27","2022-12-27"]
[null,4,{"$nulls":4},"2022-12-27","2022-12-27","2022-12-27"]
["日常",1,{"$nulls":4},"2022-12-27","2022-12-27","2022-12-27"]
[null,2,{"$nulls":4},"2022-12-27","2022-12-27","2022-12-27"]
[null,3,{"$nulls":4},"2022-12-27","2022-12-27","2022-12-27"]
[null,4,{"$nulls":4},"2022-12-27","2022-12-27","2022-12-27"]
[]
[null,null,"2022-12-05"]
["感测系统",1,"设计方案","完成设计方案初稿",null,null,"2022-12-27","2022-12-27","2022-12-27"]
[null,{"$f":"B18+1","v":2},null,"设计方案讨论及修改",null,null,"2022-12-27","2022-12-27","2022-12-27"]
[null,{"$f":"B19+1","v":3},null,"设计方案定稿",null,null,"2022-12-27","2022-12-27","2022-12-27"]
[null,4,{"$nulls":4},"2022-12-27","2022-12-27","2022-12-27"]
["日常",1,{"$nulls":4},"2022-12-27","2022-12-27","2022-12-27"]
[null,2,{"$nulls":4},"2022-12-27","2022-12-27","2022-12-27"]
[null,3,{"$nulls":4},"2022-12-27","2022-12-27","2022-12-27"]
[null,4,{"$nulls":4},"2022-12-27","2022-12-27","2022-12-27"]
[]
[]
[]
[null,null,"2022-12-05"]
["感测系统",1,"设计方案","完成设计方案初稿",null,null,"2022-12-27","2022-12-27","2022-12-27","C"]
[null,{"$f":"B30+1","v":2},null,"设计方案讨论及修改",null,null,"2022-12-27","2022-12-27","2022-12-27","C"]
[null,{"$f":"B31+1","v":3},null,"设计方案定稿",null,null,"2022-12-27","2022-12-27","2022-12-27","C"]
[null,4,{"$nulls":4},"2022-12-27","2022-12-27","2022-12-27","C"]
["日常",1,{"$nulls":4},"2022-12-27","2022-12-27","2022-12-27","C"]
[null,2,{"$nulls":4},"2022-12-27","2022-12-27","2022-12-27","C"]
[null,3,{"$nulls":4},"2022-12-27","2022-12-27","2022-12-27","C"]
[null,4,{"$nulls":4},"2022-12-27","2022-12-27","2022-12-27","C"]