{"text_format":"2","workbook":"xlsx","n_sheets":2,"sheets":["说明","2023"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":0,"comments":1,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"说明","index":0,"n_rows":9,"n_cols":2,"rows_kept":9,"cut":false,"hidden":false,"merged":[[0,0,0,1]]}
["小组月度计划/报告填写说明"]
[1,"计划的制定和执行是一个不断细化的过程；"]
[2,"月计划、周计划和日计划的区别在于时间控制的粒度不同；"]
[3,"正常情况下，月度计划与周计划、日计划有相同的任务范围；"]
[4,"月度计划由组长负责制定，月度计划的时间控制粒度为周，因此，制定月度计划时，直接将任务填写到本月相应的周计划中；"]
[5,"在实施某个周计划之前，组长须根据情况将周计划做必要的细化分解，组员根据小组的周计划将个人的任务分解到天，填写到个人的周计划中；"]
[6,"在计划实施过程中，组长须根据实际情况调整本周后面的周计划，如将后面的周计划任务提前实施，或在后面的周计划中插入新的任务；"]
[7,"在计划实施过程中，组长重点关注计划的执行情况，协助组员解决好关键路径上的任务，注意防范风险；"]
[8,"每周计划中未完成的任务（包括计划的、临时添加的、提出的问题和建议）需要标红，以便以后追踪。"]

{"sheet":"2023","index":1,"n_rows":35,"n_cols":12,"rows_kept":35,"cut":false,"hidden":false,"merged":[[0,0,0,11],[2,0,2,11],[3,0,3,11],[5,0,5,11],[8,0,8,11],[12,0,12,11],[6,0,7,0],[9,0,11,0],[13,0,14,0],[18,0,20,0],[22,0,23,0],[25,0,26,0],[28,0,29,0],[31,0,32,0],[18,1,19,1],[22,1,23,1],[28,1,29,1],[31,1,32,1],[6,2,7,2],[9,2,11,2],[13,2,14,2],[18,2,19,2],[22,2,23,2],[25,2,26,2],[28,2,29,2],[31,2,32,2],[6,10,7,10],[9,10,11,10],[13,10,14,10],[18,10,20,10],[22,10,23,10],[25,10,26,10],[28,10,29,10],[31,10,32,10]]}
["软件感测部门工作计划"]
[]
["状态代码：C- 已完成；I- 进展中；X- 未开始；D- 延期已完成；"]
["一、计划任务情况及执行情况"]
["项目","编号","任务名称","详细说明","技术路线","检验标准","计划开始时间","计划完成时间","实际完成时间","完成情况","负责人","备注"]
[]
["工程",1,"出口单片机\n楚天系统测试","出口单片机重写","c++","现场联调测试","2023-01-03","2023-01-13",null,"x","胡力"]
[null,2,null,"列举测试清单",null,"现场测试","2023-01-11","2023-01-13",null,"x"]
[]
["工程",1,"楚天项目终端崩溃问题\n楚天终端弹窗修改\n解决后台监控程序假死问题","找到原因，并解决",null,null,"2022-12-30","2022-12-31",null,"I","王康"]
[null,2,null,"修改弹窗提示，人性化",null,null,"2022-12-30","2022-12-31","2022-12-30","C"]
[null,3,null,"采用线程池解决删库不成功问题",{"$nulls":5},"I"]
[]
["工程",1,"开发出口排队信息界面","开发",null,null,"2023-01-02","2023-01-06",null,"X","王康"]
[null,{"$f":"B14+1","v":2},null,"现场调试",null,null,"2023-01-09","2023-01-13",null,"X"]
[]
["测量",1,"楚天夹持杆雷达掉线问题","现场调试",null,null,"2023-01-03","2023-01-03",null,"I","曾志文"]
[]
["测量",1,"c2入口外侧安装速腾聚创雷达","开发",null,null,"2023-01-04","2023-01-13",null,"I","唐有辰"]
[null,null,null,"测试",null,null,"2023-01-14","2023-01-20",null,"X"]
[null,2,"测试速腾雷达稳定性","测量180°遮挡情况下24小时运行情况",null,null,"2023-01-04","2023-01-13",null,"I"]
[]
["测量",1,"开发贵阳项目入口测量程序，基于速腾聚创16线","开发",null,null,"2023-01-23","2023-02-24",null,"X","唐有辰"]
[null,null,null,"测试",null,null,"2023-02-27","2023-03-10",null,"X"]
[]
["工程",1,"增加指令可视化","开发",{"$nulls":5},"x","王康","先确定需求，2023/2/1号开始"]
[null,{"$f":"B26+1","v":2},null,"现场调试",{"$nulls":5},"x"]
[]
["工程","ZX0123002-S001","1，厦门维保项目修改终端，配置服务器，修改指令检查与入队逻辑","开发",{"$nulls":5},"x","王康"]
[null,null,null,"现场调试",{"$nulls":5},"x"]
[]
["工程","ZX0123002-S002","1，厦门维保开发长条屏提示\n2，厦门维保增加与收费系统对接功能","开发",{"$nulls":5},"x","王康"]
[null,null,null,"现场调试",{"$nulls":5},"x"]
[]
["工程","ZX0123002-S002","修改调度节点，对接厦门维保项目plc",{"$nulls":6},"x","胡力"]